## Sheet1
NO | TASK | START DATE | DAYS TO COMPITE
Task1 | Find defination related to society and more detail about project | 2017-01-01 | 20
Task 2 | Find another system related to us and find similar tools from them | 2018-01-21 | 15
Task 3 | Get review from user and to ask them what they want from the | 2018-02-05 | 10
Task 4 | list out main feature of system and what are the requirement | 2018-02-15 | 9
Task 5 | calculate analysis,feasibility study and requirements elicitation | 2018-03-01 | 18
Task 6 | web map and user story board | 2018-03-11 | 5
Task 7 | UML diagram | 2018-03-16 | 7
Task 8 | dividing work between group member | 2018-03-23 | 23
Task 9 | work on wireframe | 2018-03-29 | 6
Task 10 | coding | 2018-04-02 | 10
Task 11 | configuration and debugging | 2018-04-10 | 6
Task 12 | testing | 2018-04-17 | 12
Task 13 | outcome of usability evalution | 2018-04-30 | 10
42736